## Slide 1: Green Dot AML Project Overview
June 2025

## Slide 2
GD Lookback Scope
Green Dot Bank (“Green Dot”) engaged Deloitte Transactions and Business Analytics LLP (“DTBA”) as an independent third-party to assess whether suspicious activity involving high-risk customers or transactions at, by, or through the bank were identified and reported in accordance with DTBA’s understanding of applicable Suspicious Activity Reporting (“SAR”) regulatory requirements
Assess Green Dot’s product offerings | Assess Green Dot’s products to identify applicable regulatory and industry Anti-Money Laundering (“AML”) red flags/typologies
Develop Rules | Develop rules/parameters to address the identified money laundering red flags/typologies
Generate rule instances and cases | Apply rules/parameters to Green Dot’s provided August 1, 2021 – October 31, 2022 transactional data to generate potential alerts and customer account-based cases
Conduct Transaction Monitoring Lookback | Conduct a review of the generated alerts and cases to identify potentially suspicious activity and escalate to Green Dot for SAR consideration
Final Report | Prepare a Lookback report detailing findings of the Lookback
More details on the alert generation methodology, customer identification process, and rule development can be found in the Appendix.

## Slide 3
Phase I: Data Preparation and Rules Configuration
Phase II: Case Investigation and Resolution
Phase III: Final Report
Lookback Approach
Objective
Activities
GD Lookback Approach
DTBA will perform Transaction Monitoring Lookback (the “Lookback”) activities using a three-phased approach. DTBA completed Phase 1 in May 2025 and is submitting the scope and rules to the Federal Reserve Bank (“FRB”) prior to starting on the case investigations in Phase 2.
Complete: 7 months
Estimated timeline: 6 to 7 months
Estimated timeline: 6 weeks
Investigate cases to identify potentially suspicious activity
Investigate cases generated in Phase 1 in accordance with investigation protocols and procedures
Disposition cases as no further action or potentially suspicious (escalation)
Conduct quality control review activities to monitor adherence to protocols, procedures, and the soundness of case dispositions
Escalate potentially suspicious cases to Green Dot for SAR consideration and final disposition
Complete final Lookback report detailing results of the Lookback
Draft final report that includes:
  The methodology used to generate alerts and cases and conduct the Lookback
  Investigation results, including a breakdown of no further action cases and cases escalated to Green Dot for SAR consideration
  An assessment of cases recommend for escalation including common red flags, typologies, and rule instances
Share the draft report with Green Dot and the FRB
Update the report based on feedback received from Green Dot (limited to factual accuracy) and submit the final report to the FRB
Create Lookback environment, apply rules, and develop investigation protocols
Receive Transactions from the covered period from Green Dot, standardize, and load the data into DTBA’s technical environment
Assess Green Dot’s products against red flags/typologies from regulatory and industry sources for applicability
Develop rules based on applicable red flags
Apply rules to in-scope activity to generate alerts and create customer-account based cases
Load cases into DTBA’s Enterprise Case Manager (“ECM”) tool customized for the Lookback
Create Lookback and Quality Control (“QC”) procedures, investigation protocols, and training
Submit rules, alerts, and customer cases to FRB for non-objection

## Slide 4
Team lead
QC analyst
QC analyst
QC analyst
QC analyst
QC analyst
Analyst
Production Team Structure
Team lead
QC analyst
QC analyst
QC analyst
QC analyst
QC analyst
Analyst
QC analyst
QC analyst
QC analyst
QC analyst
QC analyst
Analyst
QC analyst
QC analyst
QC analyst
QC analyst
QC analyst
Analyst
Team Lead (TL) (1 TL per location depending on team size) | Continuously monitor progress and Analyst performance; hold team members accountable and address performance issues Communicate progress, share learnings, and discuss open issues & questions with Leadership and other Team Leads (through formal or informal meetings) Apply site-specific guidelines (e.g., working hours, technology/device policies, and locations) Hold teams accountable to performance metrics and counsel those with development opportunities
Quality Control | Evaluate field level inputs and supporting documentation against policies/procedures Identify material errors within reviews and return to Analysts Ensure daily/weekly team targets are being met (QC reviews, Analyst throughput) Deliver timely feedback to Analysts in order to correct customer file errors and inconsistencies Conduct continuous improvement coaching to Analysts and identify candidates for QC Sampling Escalate file level issues identified by the Analyst to the Team Lead
Analysts | Perform and document review/alert in accordance with guidance & procedures Achieve throughput targets by completing cases Attain quality targets by conducting a holistic review and double-checking customer file prior to submission Communicate with QC when unable to achieve production targets and explain the barrier(s) to production
High level Responsibilities
Accountability. Take ownership of timely completion and quality of reviews
Collaborate: Work together across levels to ensure effective completion of reviews
Consistency and dedication: Given the nature and duration of the project it is critical that you provide a consistent level of support and dedicate the time needed to meet the targets communicated by leadership team
Key attributes
Team Roles & Responsibilities

## Slide 5
Topic | Description
Communications | Be careful and aware of all messages you send on the GreenDot system. Do not use any inappropriate language Do not send emails from GreenDot to your Deloitte email Do not work on client deliverables that contain sensitive/proprietary data on the Deloitte system – please ensure that you’re working on client work on the GreenDot network
Training | All resources will be assigned mandatory trainings once onboarded and periodically throughout the lifecycle of the project Keep an eye out for training emails or newly assigned trainings and complete all trainings within required deadlines. When trainings are complete, notify your Team Lead/Manager so we can track completion accordingly.
Hours | Bill the hours you work and work the hours you bill; If you think you will exceed scheduled hours for a week, speak to your Team Lead/Manager so adjustments can be made accordingly Time spent not related to the project should be charged to applicable non-client code (e.g., GAA, CED, etc.) Track hours on the Deloitte-side Teams site All time must be submitted on a weekly basis
PTO | Communicate PTO requests with your Team Lead/Manager as early as possible, post approval update the GreenDotCorp_PTO Tracker.xlsx and outlook calendars. Ensure appropriate coverage for any upcoming deliverables or work that may be impacted by PTO.
General Guidelines